WESTERN PACIFIC UNIVERSITY

CMN224 / CMP224 Software Engineering — Week 6

Estimation Workshop

In session · individual work on YOUR Task 2 client · output IS Task 2 sections 2.1–2.3

| Item | Details |
| --- | --- |
| Linked to | Week 6 lecture — Estimation & the Work Schedule (ULO3) |
| Bring | Your Week 5 architecture (Lab 4) and your Week 3 increment plan (Lab 3) |
| Time | 120 minutes: 30 breakdown · 35 estimate · 20 calendar · 25 schedule · 10 commit |
| Submission | This worksheet to Moodle AND committed to week06/ in your Git portfolio |
| Counts toward | Nothing directly — but it drafts 15 of the marks in Task 2 |

You cannot estimate what you have not designed. Work from your Week 5 package and deployment diagrams: each component is a natural work item. If you did not complete Lab 4, do a rough breakdown from your SRS instead and note that as an assumption.

Part A — Break down Increment 1 (30 min)

Take Increment 1 only from your Week 3 plan — the slice that is independently usable. Decompose it until every task is between 2 and 16 hours. Aim for 8–12 tasks.

Do not forget: unit tests · durability/failure testing · code review · client review and rework · documentation · installation and handover. In the worked example these came to 39% of the total.

Breakdown (Increment 1 = student registration and record management, from Lab 3): the ten tasks are listed in the Part B table. Tasks 1–5 are the build work; tasks 6–10 are the non-coding items (unit tests, durability testing, code review, client review and rework, documentation and handover). Assumption: my Week 5 architecture (Lab 4) was not to hand, so I broke the work down from the Lab 3 scope and the likely components — database, registration screen, record search/edit, login and roles.

Part B — Estimate each task (35 min)

For each task give three numbers in hours. O = everything goes right. M = a normal day. P = the realistic bad case (about one time in twenty), not the apocalypse.

E = ( O + 4M + P ) ÷ 6          SD = ( P − O ) ÷ 6

| # | Task | O | M | P | E | SD | Assumption behind it |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Project + repo setup, confirm Increment 1 scope | 2 | 3 | 6 | 3.33 | 0.67 | Git repo and tooling already familiar; scope from Lab 3 |
| 2 | Data model + local database (students, guardians, classes) | 4 | 7 | 14 | 7.67 | 1.67 | Single-school, one-machine database; no cloud |
| 3 | Student registration screen with validation | 6 | 10 | 20 | 11.00 | 2.33 | Widest spread: many fields and validation rules |
| 4 | Search, view and edit student records | 5 | 8 | 16 | 8.83 | 1.83 | Search by name/ID; edits must be logged |
| 5 | User login + roles (administrator / teacher) | 3 | 5 | 10 | 5.50 | 1.17 | Two roles only; simple password login |
| 6 | Unit tests | 4 | 6 | 10 | 6.33 | 1.00 | Non-coding. Tests for validation and database code |
| 7 | Data-loss / power-failure test + backup and restore | 3 | 5 | 12 | 5.83 | 1.50 | Non-coding. Power cuts are common in PNG |
| 8 | Code review | 2 | 3 | 6 | 3.33 | 0.67 | Non-coding. Peer or self-review against checklist |
| 9 | Client review + rework | 3 | 6 | 14 | 6.83 | 1.83 | Non-coding. Depends on staff being free to review |
| 10 | User guide + install, training and handover at school | 4 | 6 | 14 | 7.00 | 1.67 | Non-coding. Travel to school; training around timetable |

Total E = 65.67 h          Combined SD = √(sum of SD²) = 4.82 h

Check: sum of “most likely” alone = 59.0 h; PERT expected = 65.7 h — a 11% gap. Honest range = 61–70 h. Non-coding work (tasks 6–10) = 29.3 h, 45% of the job.

Note: the combined SD is NOT the sum of the SDs — square each one, add them, then take the square root. Risks partly cancel out.

Part C — Convert to a calendar (20 min)

| Question | Your answer |
| --- | --- |
| How many PRODUCTIVE hours per week can you truly give this project? (Count your other units.) | 10 productive hours per week. This is what I can honestly give after my other units, and it matches the worked example. |
| Total E ÷ productive hours per week = how many weeks? | 65.67 ÷ 10 = 6.6 weeks. |
| Same calculation using E − SD and E + SD → your honest range | E − SD = 60.8 h → 6.1 weeks; E + SD = 70.5 h → 7.0 weeks. Honest range = 6.1–7.0 weeks (61–70 h). |
| Which PNG factors will stretch this? (client availability, travel, power, term dates, holidays) | School terms and holidays (client review and staff training only possible when staff are on-site); teachers’ and administrators’ limited availability for reviews; power cuts and unreliable internet (testing, Git pushes, remote meetings); travel to the school for installation and handover; approval cycles with school management. |
| Adjusted finish, stated as a range | About 7–9 weeks (the 6.1–7.0 week range plus 1–2 weeks for the PNG factors). This is longer than the 3 weeks in my Lab 3 plan, which was an early rough guess made before any task-level estimate — the Lab 3 duration should now be revised. |

Part D — Build the schedule (25 min)

Lay out all three increments with client-visible milestones. A milestone must be something your client could verify themselves — “the bursar records a real payment and prints a receipt”, never “backend complete”.

| Increment | What it delivers | Milestone the client can see | Weeks |
| --- | --- | --- | --- |
| 1 | Student registration and record management: registration screen, search/view/edit of records, login and roles, local database, tested, installed and handed over. | The school registrar registers a real new student and guardian, finds the student again by name, edits the contact details, and the record is still there after the computer is deliberately switched off and restarted. | Weeks 1–8 (7–9 wks; 61–70 h at 10 h/week plus PNG allowance) |
| 2 | Attendance tracking and class management: class lists, daily attendance marking, weekly attendance view per class. | A teacher marks today’s attendance for a real class and the head teacher views that class’s attendance for the week. | Weeks 9–13 (about 5 wks; scaled from Increment 1 by the Lab 3 size ratio) |
| 3 | Reporting, analytics and printable summaries: attendance summaries, class lists and student reports built from Increment 1–2 data. | The head teacher prints a term attendance summary and a class list from the school’s real data for a management meeting. | Weeks 14–18 (about 5 wks; widest range as report needs will change after Increment 1) |

Part E — Commit (10 min)

- Put this worksheet into week06/ in your portfolio.

git add week06/

git commit -m "Add increment 1 estimate and delivery schedule"

Reference — the worked example from the lecture

Kina Ridge fee system, Increment 1. Use it to check your arithmetic method, not to copy numbers.

| Task | O | M | P | E | SD |  |
| --- | --- | --- | --- | --- | --- | --- |
| Project + repo setup | 2 | 3 | 6 | 3.33 | 0.67 |  |
| Data model + local database | 4 | 6 | 12 | 6.67 | 1.33 |  |
| Payment entry screen | 6 | 10 | 20 | 11.00 | 2.33 | widest spread |
| Receipt numbering + printing | 4 | 8 | 16 | 8.67 | 2.00 |  |
| Authorisation (bursar / head) | 3 | 5 | 10 | 5.50 | 1.17 |  |
| Unit tests | 4 | 6 | 10 | 6.33 | 1.00 | non-coding |
| Power-failure durability test | 2 | 4 | 10 | 4.67 | 1.33 | non-coding |
| Client review + rework | 3 | 6 | 14 | 6.83 | 1.83 | non-coding |
| Install + handover at school | 2 | 4 | 10 | 4.67 | 1.33 | non-coding |
| TOTAL |  |  |  | 57.67 | 4.58 |  |

Sum of “most likely” alone = 52.0 h. PERT expected = 57.7 h — the 11% gap is optimism made visible. Honest range = 53–62 h. Non-coding work = 22.5 h, 39% of the job. At 10 productive hours a week that is about 5.8 weeks.